## 📋 Job List
AGERO ¦ Job List
Updated by Bernie every Monday morning before the 9:15 huddle. All team members: read only.
Job Name | Classification | Owner | Stage | Status | Key Date | Client | Value ($) | Notes
Project Alpha | Active Delivery | Bernie | On Site | Green | 30 Jun 2026 | Client A | $850,000
Project Beta | Active Delivery | Shaq | On Site | Amber | 15 Aug 2026 | Client B | $420,000 | Programme risk: structural drawings
Project Gamma | Pre-Construction | Shaq | Design Dev | Green | 1 Sep 2026 | Client C | $600,000
Project Delta | Pre-Construction | Bernie | Tender | Green | 20 Jul 2026 | Client D | $1,200,000 | Subcontractor pricing due
Prospect: Omega Tower | Prospect: Tier 1 | Bernie | Submission Prep | Amber | 10 Jul 2026 | Prospect E | $2,500,000 | Complex fitout; Maya leading design
Prospect: Suite 12 | Prospect: Tier 2 | Shaq | EOI Prep | Green | 5 Jul 2026 | Prospect F | $180,000 | Standard fitout
Prospect: Level 8 | Prospect: Tier 2 | Maya | Concept Design | Green | 12 Jul 2026 | Prospect G | $250,000
Project Epsilon | On Hold | Bernie | Client Hold |  | TBC | Client H | $700,000 | Client paused pending board approval

## ℹ️ How to Use
AGERO ¦ Huddle Framework ¦ How to Use
WHO DOES WHAT
Job List | Bernie updates every Monday morning before the huddle. Add new jobs, update status (Green/Amber/Red), and set ownership. All team members read from this tab.
Daily Prep tabs | Each person (Bernie, Shaq, Maya) fills in their own tab before 9:00 am every day. One row per job they own or contribute to. The three questions: what needs to move, what is blocking me, what do I need from the team.
Weekly Brief tabs | Each person completes their weekly tab on Monday morning before the huddle. One row per active job or live prospect. Bernie reviews all three before the Monday 9:15.
THE HUDDLE
Format | 15 minutes. Standing. Bernie goes first (Director context + his jobs). Then Shaq (his jobs). Then Maya (her design workstream). Bernie closes with confirmations and any priority adjustments.
Standard for updates | Name the job. State what is moving. State what is blocked. State what you need. If you have nothing to say beyond 'all good', you have not prepared.
Bernie's role | Confirm clear plans. Redirect unclear ones. Respond to legitimate escalation (owner has a recommendation). Push back dependency questions: 'What do you recommend?'
CLASSIFICATIONS
Active Delivery | Project under contract and in delivery. Full daily attention from the job owner.
Pre-Construction | Awarded but not on site, or in tender/design development. Progressed to programme.
Prospect: Tier 1 | Large or complex. Bespoke submission. Bernie classifies. Treated with near-project discipline.
Prospect: Tier 2 | Standard. Fits within established approach. Efficient processing.
On Hold | Paused by client or external circumstance. Not discussed daily unless status changes.
STATUS (RAG)
Green | On programme and budget. No material risks.
Amber | At risk. Issue identified but manageable. Owner has a plan.
Red | Blocked or off programme. Bernie's attention required today.
GOOGLE SHEETS NOTE
Uploading | Upload this file to Google Drive and open with Google Sheets. All formatting, dropdowns, and filters will transfer.
Sharing | Share with Shaq and Maya as Editors. They can fill in their own tabs. The Job List tab should be treated as Bernie's domain — communicate this directly rather than relying on sheet protection.

## 📋 Bernie
AGERO ¦ Bernie ¦ Weekly Brief & Daily Prep
Set your weekly direction above, then log daily execution below. Both sections updated in this one tab.
WEEKLY MISSION BRIEF — Complete every Monday morning before the 9:15 huddle
Job / Prospect | Week Of | Classification | Success by Friday? | Top 3 actions this week | External contributors | Decisions I own | Where I need Bernie
Project Alpha | 2026-06-08 | Active Delivery | Structural package approved; programme on track | 1. Approve structural package 2. Client progress meeting 3. Review variation 004 | Engineer: drawings by Wed Subcontractor: pricing by Fri | Variations up to $15k Daily site decisions | Variations above $15k Client relationship decisions
Prospect: Omega Tower | 2026-06-08 | Prospect: Tier 1 | Submission draft complete and reviewed | 1. Draft narrative sections 1–2 2. Review Maya's concept visuals 3. Internal review Thursday | Maya: concept visuals by Tue VA: format document by Thu | Narrative content Subcontractor selection | Final submission sign-off Client presentation
DAILY PREP LOG — Complete before 9:00 am every day. One row per job.
Job / Prospect | Date | What needs to move today? | What is blocking me? | What do I need from the team? | Who from? | Resolved? | Notes
Project Alpha | 2026-06-08 | Review structural package with engineer | Engineer has not sent revised drawings | Confirm design intent on grid line C | Maya | No
Prospect: Omega Tower | 2026-06-08 | Draft submission narrative sections 1 and 2 | Need Maya's concept visuals to complete | Concept visuals needed by 11am | Maya | No | Tier 1 — high priority

## 📋 Shaq
AGERO ¦ Shaq ¦ Weekly Brief & Daily Prep
Set your weekly direction above, then log daily execution below. Both sections updated in this one tab.
WEEKLY MISSION BRIEF — Complete every Monday morning before the 9:15 huddle
Job / Prospect | Week Of | Classification | Success by Friday? | Top 3 actions this week | External contributors | Decisions I own | Where I need Bernie
Project Beta | 2026-06-08 | Active Delivery | Concrete pour complete; next trade on programme | 1. Confirm pour sequence 2. Issue RFI on ceiling heights 3. Programme update to Bernie | Foreman: confirm sequence Mon Subcontractor: hydraulics by Wed | Daily site coordination RFI responses Variations up to $5k | Variations above $5k Programme slippage beyond 5 days Client comms
Prospect: Suite 12 | 2026-06-08 | Prospect: Tier 2 | EOI document submitted | 1. Complete EOI draft by Wed 2. Bernie review Thu 3. Submit Fri | VA: format EOI by Thu | EOI content and pricing Subcontractor approach | Bernie review before submission
DAILY PREP LOG — Complete before 9:00 am every day. One row per job.
Job / Prospect | Date | What needs to move today? | What is blocking me? | What do I need from the team? | Who from? | Resolved? | Notes
Project Beta | 2026-06-08 | Confirm concrete pour sequence with foreman | Structural drawings still at risk | Call engineer if drawings not by noon | Bernie | No
Prospect: Suite 12 | 2026-06-08 | Complete EOI document draft |  | Review draft before submission | Bernie | No | Due Friday

## 📋 Maya
AGERO ¦ Maya ¦ Weekly Brief & Daily Prep
Set your weekly direction above, then log daily execution below. Both sections updated in this one tab.
WEEKLY MISSION BRIEF — Complete every Monday morning before the 9:15 huddle
Job / Prospect | Week Of | Classification | Success by Friday? | Top 3 actions this week | External contributors | Decisions I own | Where I need Bernie
Design: Project Alpha | 2026-06-08 | Active Delivery | Revised ceiling plan issued; RFIs complete | 1. Issue ceiling plan Tue 2. Resolve RFI 012 with engineer 3. Coordinate FF&E schedule | Engineer: coordination drawing by Wed Architect: FF&E confirmation by Thu | Design coordination Document issue Consultant management | Client finish preferences Scope changes affecting cost
Prospect: Omega Tower | 2026-06-08 | Prospect: Tier 1 | Two concept options complete and approved by Bernie | 1. Concept option A — Mon 2. Concept option B — Tue 3. Bernie review Wed | Architect: preliminary sketch by Mon | Design direction within brief Consultant briefing | Brief confirmation (Bernie owns) Client presentation (Bernie presents)
DAILY PREP LOG — Complete before 9:00 am every day. One row per job.
Job / Prospect | Date | What needs to move today? | What is blocking me? | What do I need from the team? | Who from? | Resolved? | Notes
Design: Project Alpha | 2026-06-08 | Issue revised ceiling plan to Shaq | Waiting on engineer coordination | Confirm client preference on finish | Bernie | No
Prospect: Omega Tower | 2026-06-08 | Complete concept visuals for submission |  | Confirm brief scope by 9:30am | Bernie | No | Tier 1 — urgent